# Milestone ladder (each has a clear “done”)

- Boot & Toy Run

  - Do: Install deps; run toy_stream → core/loop.run(...).

  - Done when: Loop cycles without errors; telemetry prints χ, T, tail metrics; orders/fills logged.

- Real Data Ingest

  - Do: Add a real OHLCV feed (CSV/Parquet or your data vendor) into data/ingest.py; wire resampling.

  - Done when: Loop runs on historical bars; returns/vol match a quick pandas check.

- Tail Telemetry Live

  - Do: Confirm tails.Tails.update outputs Hill α, J-ratio, ESq; trigger alarm with synthetic spikes.

  - Done when: Tail alarms flip the gate temperature and reduce position sizes as per control law.

- Regime Module Swap-in

  - Do: Replace EWMA with arch GARCH-t; enable 2-state HMM if available; keep BOCPD-lite.

  - Done when: Vol states switch sensibly (low/high); BOCPD triggers on injected outliers; run-length resets.

- Heads v0 (baseline)

  - Do: Control = TSMOM; Creative = shock-follow on regime breaks.

  - Done when: Both heads produce proposals & scenario paths; gate weights (softmax) are sensible across regimes.

- Risk & Sizing v0

  - Do: CVaR-aware scoring (risk.score_cvar); ES/Hill throttles in risk.size_orders.

  - Done when: Same signals size differently across calm vs tail regimes; kill-switch thresholds configurable.

- Walk-Forward Harness

  - Do: Implement purged_kfold_indices and a simple wrapper to replay bars through the loop.

  - Done when: You can print SR, DSR, ESq, max DD for each fold; no leakage warnings.

- Memory & Consolidation

  - Do: episode_store: log high-χ/ΔF episodes; schema_registry: track candidate rules; nightly interleaved replay into LTWM.

  - Done when: Telemetry shows replay_fraction, promotion_count; promoted rules persist and are used by Control.

- Quantile Uplift (optional)

  - Do: Add LightGBM quantile model for a horizon; feed q-estimates into head edges.

  - Done when: Backtest shows calibration plots for predicted quantiles; ES at target level improves or holds.

- Paper-Trade Harness

  - Do: Add a paper broker adapter (or a no-op execution ledger with slippage); export daily PnL & risk report.

  - Done when: Runs unattended on a watchlist; daily report includes Ψ-profile: ESq, Hill α, J-ratio, τ½ after shocks, Ψ-band exits.

# “Definition of done” (system-level)

- Stability: 24-hour unattended run on live or recorded stream without exceptions.

- Risk: ES_q and max DD within your caps on out-of-sample folds; tail alarms reduce exposure automatically.

- Adaptation: After an injected regime break, τ½ to recover within your target; fewer Ψ-band exits with memory on vs off.

- Traceability: Every trade has a head, gate weight, tail metrics, and regime state logged.

# How to self-calibrate your pace (no guesswork)

- Work through Milestones 1–3, counting your actual sessions.

- Note blockers (data wrangling, dependencies, plotting, etc.).

- Use that observed “sessions per milestone” to forecast the remaining ones based on complexity you felt:

  - Low (1×): 4–5: simple glue.

  - Medium (2×): 6–7: integration & evaluation.

  - High (3×): 8–10: memory, ML uplift, paper-trade loop.

# Common time sinks (avoid these traps)

- Data quirks: timezone/roll adjustments, futures continuous series, split/roll gaps. Start with one instrument (e.g., EURUSD) until the loop is stable.

- Dependency drift: pin versions in a requirements.txt.

- Over-engineering early: keep heads simple until walk-forward metrics are flowing.

- Evaluation creep: decide primary KPIs now: ES_0.95, max DD, SR/DSR, τ½, Ψ-exits.

# Minimal session recipe (repeatable 2-hour block)

- pick 1 milestone;

- implement 1 test + 1 function;

- run toy → real data;

- log metrics;

- jot issues/todos for next session.

# file: docs/IMPLEMENTATION_CHECKLIST.md

# Trident G-Loop Trader — Milestone & Acceptance Checklist

> Tick each box only when the **acceptance test** passes. Keep notes inline.

---

## 0) Environment & Repo

- [ ] `python -V` shows 3.10+; `pip install -r requirements.txt` succeeds

- [ ] `pytest -q` (if present) runs without errors

- [ ] Pin versions saved (e.g., `requirements.txt`)

**Notes:**

---

## 1) Boot & Toy Run

**Goal:** end-to-end loop runs on toy stream.

- [ ] `toy_stream` → `core.loop.run(...)` cycles ≥ 1,000 steps without exception

- [ ] Telemetry logs **χ**, **T(χ)**, **ζ(Hill)**, **J-ratio**, **ES(ΔF)**

- [ ] Orders/fills objects emitted per step

**Notes:**

---

## 2) Real Data Ingest

**Goal:** loop runs on historical OHLCV for ≥1 symbol.

- [ ] `data/ingest.py` loads bars (CSV/Parquet) and computes `returns`

- [ ] Spot check: `np.std(returns)` matches pandas calc (±1e-9)

- [ ] Loop runs full file without exception

**Artifacts:** 1 parquet sample in `data/`

**Notes:**

---

## 3) Tail Telemetry Live

**Goal:** alarms drive the controllers.

- [ ] Inject synthetic spike → tail module sets `alarm=True`

- [ ] On alarm: **T(χ)↑** and position **size↓** (visible in logs)

- [ ] Thresholds configurable in `params.yaml` (`hill_min`, `j_ratio_max`, `es_max`)

**Notes:**

---

## 4) Regime Module Swap-in

**Goal:** realistic vol & regime signals.

- [ ] `arch` GARCH-t returns `sigma`; EWMA fallback works if `arch` missing

- [ ] 2-state HMM updates state; BOCPD-lite resets `run_length` on shocks

- [ ] State/thresholds logged in telemetry

**Notes:**

---

## 5) Heads v0 (Control & Creative)

**Goal:** both heads produce proposals + scenarios.

- [ ] Control: TSMOM direction = sign(mean multi-horizon momentum)

- [ ] Creative: shock-follow activates only on `regime_break=True`

- [ ] Each proposal includes `direction`, `edge`, and 500-path `scenario_pnl`

**Notes:**

---

## 6) Risk & Sizing v0

**Goal:** CVaR-aware scoring & ES/Hill throttles.

- [ ] `risk.score_cvar` returns `{score, edge, es}`

- [ ] Calm vs tail regime → same signals sized differently (logged qty change ≥ 30%)

- [ ] Global caps adjustable in `params.yaml` (`vol_target`, `kelly_fraction`, `es_star`)

**Notes:**

---

## 7) Walk-Forward Harness

**Goal:** leakage-safe evaluation.

- [ ] `purged_kfold_indices(n,k,embargo)` returns k splits; no index overlap with test + embargo

- [ ] For each fold: compute **Sharpe**, **Deflated Sharpe (DSR)**, **ES\_q**, **Max DD**

- [ ] Report table saved to `backtest/results/*.csv`

**Notes:**

---

## 8) Memory & Consolidation (Episodic + Schema)

**Goal:** Gf→Gc consolidation wired.

- [ ] High-χ / high-|ΔF| segments logged to `EpisodeStore` (check buffer length > 0)

- [ ] Nightly consolidate: **replay_fraction** ~ config (e.g., 0.30 ± 0.05)

- [ ] `SchemaRegistry` promotes ≥1 candidate with audit line in telemetry

- [ ] **A/B test:** memory **ON** vs **OFF** → **ES\_0.95(ΔF)** lower and **τ½** after regime break shorter with memory **ON**

**Notes (attach A/B numbers):**

---

## 9) Quantile Uplift (optional)

**Goal:** risk-aware forecasts improve calibration.

- [ ] LightGBM quantile model trains (≥300 samples) without error

- [ ] Calibration plot: predicted q vs realized exceedance (slope ~1 ± tolerance)

- [ ] Backtest: ES\_q improves or holds vs baseline at same DD

**Notes:**

---

## 10) Paper-Trade Harness

**Goal:** unattended run & daily report.

- [ ] Paper execution ledger records price/qty/slippage; no exceptions ≥ 24h

- [ ] Daily report exported (`reports/YYYY-MM-DD.html`): Ψ-profile (χ, T, ζ, J, ES), SR/DSR, Max DD, τ½, Ψ-band exits

- [ ] Kill-switch triggers on ES or DD breach (dry-run tested)

**Notes:**

---

## System-Level Definition of Done (check all)

- [ ] **Stability:** 24h unattended run passes

- [ ] **Risk:** ES\_q and Max DD within caps on out-of-sample folds

- [ ] **Adaptation:** τ½ after injected regime break meets target

- [ ] **Traceability:** every trade logged with head, gate weight, tail metrics, regime state

**Sign-off:**

---

## Quick Run Commands (examples)

- [ ] Toy run: `python -m tridentg_trader.scripts.smoke` (or your notebook cell)

- [ ] Backtest: `python -m tridentg_trader.scripts.walkforward --symbol EURUSD --k 5`

- [ ] Paper trade: `python -m tridentg_trader.scripts.paper --universe configs/markets.yaml`

*(Create `scripts/` wrappers as you go; adjust names to your setup.)*

---

## Bug Log (rolling)

- [ ] Issue / Repro / Expected / Fix / Commit

**Total Estimated Time Range: 80 - 160 hours**

This range accounts for a proficient Python developer familiar with basic financial concepts and libraries like NumPy/Pandas, but who may be learning some of the specific libraries (`arch`, `hmmlearn`, `ruptures`) for the first time.

Here’s how that time breaks down into phases:

---

### Phase 1: Core Loop & Basic Heads (20-40 hours)

**Goal:** A functioning, simplified version of the loop that can run on a toy data stream.

*   **~5-10h:** Set up the repo structure, config files, and the main `GLoop` class skeleton with the `one_step` method.

*   **~5-10h:** Implement the `Dials` and `gate.softmax` logic. Code the `toy_stream` data generator.

*   **~5-10h:** Build the simple `ControlHead` (basic TSMOM) and `CreativeHead` (shock-following).

*   **~5-10h:** Implement naive `sizing` (simple vol-targeting) and a mock `Execution` module. Get the entire loop running end-to-end on toy data, logging basic telemetry.

**Output:** You have a working "engine".-

---

### Phase 2: Telemetry & Risk Infrastructure (25-50 hours)

**Goal:** Integrate the advanced risk metrics that make the system robust.

*   **~10-15h:** Implement the `Tails` module. This is crucial. Getting the Hill estimator, J-ratio, and empirical ES working reliably will take time.

*   **~10-20h:** Implement the `Regimes` module. Integrating `arch` for GARCH vol and `hmmlearn` for the HMM requires reading docs and debugging fits.

*   **~5-15h:** Upgrade the `risk.score_cvar` function and `risk.size_orders` to be truly sensitive to the `tails_out` telemetry (the ES throttle).

**Output:** The system now understands volatility and tail risk, making it far safer.-

---

### Phase 3: Offline Analysis & Validation (15-30 hours)

**Goal:** Build the tools to check if it's working and not fooling itself.

*   **~5-10h:** Implement the `walkforward.purged_kfold_indices` function.

*   **~5-10h:** Code the `metrics.deflated_sharpe` function and basic performance reporting.

*   **~5-10h:** Run initial backtests on historical data, analyze results, and fix the first major round of bugs.

**Output:** You can trust your results more and have a scientific way to test improvements.-

---

### Phase 4: Consolidation & Learning (20-40 hours)

**Goal:** Implement the "Gf→Gc pipeline" that makes the system adaptive.

*   **~5-10h:** Build the `EpisodeStore` for logging high-stress episodes.

*   **~10-20h:** Implement the `SchemaRegistry.promote_if_robust` logic with basic checks (e.g., ES improvement).

*   **~5-10h:** Build the `LTWM.update_models` method to retrain the slower models (e.g., GARCH, Quantile LGBM) on the interleaved replay batch.

**Output:** The system now learns from experience and can promote successful creative strategies to its core rule set.-

---

### Key Variables That Will Affect Your Timeline:

*   **Familiarity with Libraries:** If you've never used `arch`, `hmmlearn`, or `ruptures`, budget extra time for the learning curve. Their APIs can have quirks.

*   **Debugging & The "Data Wrangle:"** This is the biggest unknown. You will spend a significant portion of your time not writing new code, but debugging why the new code you wrote is outputting `NaN`s, has shape mismatches, or has off-by-one errors in time indices. This is normal.

*   **Historical Data Acquisition & Prep:** The estimate assumes you have a quick way to get clean price data (e.g., from a broker API, Yahoo Finance, etc.). If not, add time.

*   **Feature Engineering:** The current `FeatureBuilder` is simple. Making genuinely predictive multi-timescale features is a project in itself and could easily add 20+ hours.

*   **"Just One More Thing":** You'll constantly think of small improvements (a new metric, a better plot, a different sizing function). This can bloat the timeline if not managed.

### Recommendation: An Agile Approach

Don't try to build it all at once. Follow the phased approach:

1.  **Get Phase 1 done immediately.** A minimal working loop is incredibly motivating.

2.  **Integrate Phase 2 (Telemetry) piece by piece.** Add volatility, then tails, then the risk-sizing.

3.  **Validate with Phase 3** before worrying too much about Phase 4. You need to know your base system is sound before making it learn.

4.  **Phase 4 is the final, advanced upgrade** that will make the system truly special.

This is a solid 2-4 month project for a skilled individual working on it part-time. The result, however, won't just be a "trading strategy"; it will be a **adaptive trading agent**—a formidable personal tool. Good luck